## sprint_49_target
Days | UI test cases (modules) | BACCO Automation | Admin panel Automation Script Run | Adhoc Testing | payment Test Case Written
1 | Ad Block server | 1,2 |  | iphone: issue 9705 test |  | Done
2 | Gaming Server | 3,4 |  | android: same as 9705 test
3 | Streaming Server | 5,6 |  |  |  | In Progress
4 | Loyalty Server | 7,8
0 | Highspeed Server | 9,10 | As mush as | Depends on devlopment | As mush as | New
6 | Purchase For Friend | 11,12
7 | Favourite Server | 13,14
8 | Settings | 15,16
9 | Settings | 17,18
10 | Settings | 19

## Test Summary
Spint( 31 ) - Test Case Summary (6-11-23 -- 12-11-23)
Total testcase Written | 45
Total Execution | 41
Total Review | 63
Spint( 32 ) - Test Case Summary (13-11-23 -- 19-11-23)
Total testcase Written | 0
Total Execution | 0
Total Review | 0
Spint( 32 ) - Day 2 - Test Case Summary
Total testcase Written | 0
Total Execution | 0
Total Review | 17
Spint( 32 ) - Day 5 - Test Case Summary
Total testcase Written | 0
Total Execution | 9
Total Review | 13
Spint( 33) - Day 1 - Test Case Summary
Total testcase Written | 0
Total Execution | 1
Total Review | 14
Spint( 33) - Day 2- Test Case Summary
Total testcase Written | 28
Total Execution | 34
Total Review | 20
Spint( 33) - Day 5- Test Case Summary
Total testcase Written | 48
Total Execution | 34
Total Review | 20
Spint( 34) - Day 5- Test Case Summary
Total testcase Written | 80
Total Execution | 52
Total Review | 0
Spint( 34) - Day 10- Test Case Summary
Total testcase Written | 120
Total Execution | 75
Total Review | 0
Spint( 35) - Day 1 - Test Case Summary
Total testcase Written | 41
Total Execution | 0
Total Review | 41

## Test Target
Spint( 32 )
Written | 20 / (0)
Execution | 40 / (0)
Review | 40 / (17)